# Hardware Billing OS — Development Plan

Billing OS for Hardware & Building Materials · v1

9 October 2026

Build v1 in about 24 weeks as a cloud SaaS with an offline-capable billing counter, shipping Billing, Inventory and Ledger first, then Reports, then the AI assistant, and pilot it in 3 to 5 hardware shops before general launch.

# 1. Vision and v1 scope

Who it is for: single-location hardware and building-materials shops in Tamil Nadu (1 to 3 billing counters, 1 to 2 godowns, ₹50 lakh to ₹10 crore turnover) that sell to walk-in retail buyers, masons, contractors and smaller dealers, often on credit.

The problem it solves: today these shops use a billing tool (Vyapar, myBillBook, Tally, Marg) plus a notebook for credit and a memory for stock. Generic tools break on three things this trade does every day: buying in one unit and selling in another, quoting different rates to different customer types, and chasing credit spread across many contractors.

Positioning: “the shop’s daily business manager, not an invoice printer.” The three differentiators are the product’s spine, not add-ons:

- Smart unit conversion — buy a box of 100, sell 7 pieces; buy TMT by the tonne, sell by the rod; buy wire by the coil, sell by the metre. Stock is always exact.

- Contractor pricing — Retail, Wholesale and Contractor price lists, applied automatically by customer.

- AI business assistant — ask in Tamil or English: “Who owes me money?”, “Which products should I reorder?”

In v1: Dashboard, Billing/POS, Products & Stock, Purchases, Customer & Supplier Ledger, Reports, AI assistant, Tamil + English UI, thermal and A4 printing, WhatsApp invoice sharing and payment reminders.

Not in v1 (park for v2): multi-branch, e-invoicing (IRN) and e-way bill generation, full accounting (balance sheet, P&L with depreciation), payroll, online store, delivery vehicle tracking, FIFO/batch costing.

Design rule for every screen: a counter clerk with no training should finish a 5-line cash bill in under 30 seconds using only the keyboard.

# 2. Tech stack and architecture

Use the established stack — a FastAPI modular monolith on PostgreSQL, with a Next.js back office and a desktop billing counter that keeps billing when the internet drops.

| Layer | Choice | Why |
| --- | --- | --- |
| Backend | FastAPI modular monolith (Python 3.12), SQLAlchemy 2 + Alembic | One deployable; modules (billing, inventory, ledger, reports, ai) stay separated by package and service boundaries |
| Database | PostgreSQL 16, shared schema with tenant_id + Row-Level Security | Thousands of small shops make schema-per-tenant migrations slow; RLS keeps isolation enforced in the database |
| Jobs | Celery + Redis | Reminders, report snapshots, reorder calculations, WhatsApp sends, nightly backups |
| Back office web | Next.js (App Router) + TanStack Query + shadcn/ui | Owner and accountant screens: dashboard, reports, masters, ledger |
| Billing counter | Tauri desktop app (same React UI) + local SQLite + sync queue | Works offline, prints silently to ESC/POS thermal and A4 printers, reads USB barcode scanners as keyboard input |
| Owner mobile (v1.5) | React Native, offline-first | Dashboard, AI assistant, collections on the go |
| Messaging | MSG91 WhatsApp + SMS | Invoice PDF share, payment reminders, low-stock alerts to owner |
| Payments | Razorpay / Cashfree UPI payment links + dynamic UPI QR on bill | Faster collections; auto-match payment to invoice via webhook |
| AI | Azure GPT-4o for tool-calling, Qwen2.5 self-hosted as fallback; faster-whisper for Tamil voice queries | Model only chooses and narrates; numbers come from SQL functions |
| PDF / print | WeasyPrint for A4 GST invoices; raw ESC/POS for 2-inch/3-inch thermal | Thermal printing must be instant and not go through a browser print dialog |
| Infra | Docker Compose on a VPS (Mumbai region) to start; daily pg_dump + WAL archiving to object storage | Cheap to run during pilot; move to managed Postgres after ~200 tenants |

Offline billing rule: the counter app holds a local copy of products, prices, customers and stock for its shop. A bill made offline gets a number from a per-device series reserved in advance (for example C1/2026-27/0001), is saved locally, printed, and pushed to the server when online. The server is the source of truth for stock and ledger; conflicts (stock went negative, customer over credit limit) are flagged for the owner, never silently rejected.

How the parts connect:

- Apps (top layer): Billing counter (Tauri desktop + local SQLite, works offline, drives printers and scanners) · Back office web (Next.js: dashboard, reports, masters) · Owner mobile app (React Native, v1.5: dashboard, AI, collections).

- Backend (middle layer): one FastAPI modular monolith with six modules — Billing, Inventory, Ledger, Reports, AI assistant, Tenancy + auth. The counter talks to it through an offline sync queue; the web and mobile apps use the HTTPS JSON API.

- Data and services (bottom layer): PostgreSQL 16 (shared schema + RLS: ledgers, stock, documents) · Celery + Redis (reminders, snapshots, backups) · External services (MSG91 WhatsApp, UPI payment links, Azure GPT-4o / Qwen2.5).

# 3. Data model and key design decisions

Get four things right before writing any screen: units, price lists, the stock ledger and the party ledger. Everything else sits on top of them.

## 3.1 Smart unit conversion

- Every product has one base unit — the smallest unit you ever sell (piece, kg, metre, sq ft, litre).

- A product_units table lists every other unit with its factor to base: Box = 100 pcs, Coil = 90 m, Tile box = 8 pcs = 15.5 sq ft.

- Stock is stored only in base units, as NUMERIC(18,4). Never store “2 boxes and 37 pieces”; display it that way.

- Each unit has its own flags: can buy, can sell, own barcode, own price.

- Variable-weight items (TMT bars, angles, sheets): the factor is a default, but the bill lets the clerk enter actual weighed kg. Stock moves by the actual weight.

- Rounding rule: convert to base with 4 decimals, round money only at line total (2 decimals).

## 3.2 Contractor pricing

- price_lists: Retail (default), Wholesale, Contractor, plus any the shop adds.

- product_prices: (product, unit, price list) → selling price, with effective-from date so price history is kept.

- Each customer is assigned a price list; walk-in customers get Retail.

- Optional quantity breaks (for example contractor rate drops above 50 bags).

- Guard rails: the clerk can change a rate only within a set band; selling below purchase cost needs an owner PIN, and is logged.

## 3.3 Stock ledger

- stock_movements is append-only: every purchase, sale, return, adjustment, transfer and opening stock writes one row per product per godown, in base units, with unit cost.

- stock_balances (product × godown) is updated in the same database transaction, so reads are fast and always match the ledger.

- Costing: weighted average cost for v1 — simple for shop owners and good enough for gross margin. FIFO/batch can come later.

- Negative stock is allowed but flagged (shops often bill before the purchase entry is made).

## 3.4 Party ledger (customers and suppliers)

- One parties table with a type (customer, supplier, both), GSTIN, price list, credit limit and credit days.

- ledger_entries are append-only: invoice (debit), payment (credit), return (credit note), opening balance, adjustment.

- payment_allocations link each payment to specific invoices, which gives invoice-wise dues and ageing (0–30, 31–60, 61–90, 90+ days).

- Unallocated payments sit as “on account” and are auto-applied oldest-first unless the owner chooses otherwise.

## 3.5 GST and documents

- Each product carries HSN code and GST rate; rates are stored with an effective-from date, because rates do change (several building materials moved in the 2025 rate rationalisation).

- CGST + SGST for in-state sales, IGST when place of supply is another state; decided from customer state, not shop default.

- B2B invoice needs a valid GSTIN (format + checksum check); B2C is allowed without.

- Separate number series per document type and financial year: Invoice, Quotation, Delivery Challan, Credit Note, Purchase, Debit Note.

- Posted invoices are never edited or deleted — corrections go through a credit note or cancel-and-reissue, with an audit trail.

## 3.6 Core tables (first cut)

| Area | Tables |
| --- | --- |
| Tenant | tenants, users, roles, devices, settings, number_series |
| Catalogue | products, categories, brands, product_units, price_lists, product_prices, hsn_rates |
| Stock | godowns, stock_movements, stock_balances, stock_adjustments, stock_transfers |
| Sales | quotations, sales_invoices, sales_invoice_lines, delivery_challans, sales_returns, receipts |
| Purchase | purchase_orders, purchase_invoices, purchase_lines, purchase_returns, supplier_payments |
| Ledger | parties, ledger_entries, payment_allocations, reminders |
| Money | expenses, expense_categories, cash_sessions (open/close), bank_accounts |
| AI | ai_queries (question, tool calls, answer, feedback) |

# 4. Module build spec

Each module below lists what to build and a “done when” test you can check in the pilot shop.

## Module 1 — Fast Billing (POS)

Build:

- Product search by name (Tamil or English, typo-tolerant), code or barcode; last-used items first.

- Unit picker on each line (pcs / box / kg / rod) with live conversion to stock.

- Customer picker that loads the customer’s price list, credit limit and current dues.

- Line and bill discounts (% or ₹), round-off, GST split shown per line.

- Payment modes: cash, UPI (dynamic QR printed on bill), card, credit, and split payments.

- Hold / recall bill (customer stepped away), duplicate last bill.

- Quotations that convert to invoice in one click; delivery challans for partial or later site delivery.

- Sales returns against an invoice → credit note + stock back.

- Print: 3-inch thermal, 2-inch thermal, A4/A5 GST invoice; share PDF on WhatsApp.

- Keyboard shortcuts for every action (F2 new bill, F4 customer, F9 save and print, and so on).

Done when: a 5-line cash bill takes under 30 seconds; a credit bill that crosses the limit warns and asks for owner PIN; an offline bill syncs with no duplicate numbers.

## Module 2 — Smart Inventory

Build:

- Product master with categories, brands, units, HSN, GST, purchase price, price list rates, minimum stock and reorder quantity.

- Bulk import from Excel / Tally / Vyapar export, with a preview and error report.

- Purchase entry from supplier bill: lines in purchase units, freight and loading charges spread into cost, stock and average cost updated.

- Purchase orders and purchase returns (debit note).

- Godowns: stock per godown, transfers between godowns.

- Stock adjustments with reason codes (breakage, theft, count correction) and owner approval.

- Physical stock count: print or phone count sheet, enter counts, review variance, post.

- Price history per product (purchase and selling), barcode label printing.

- Low-stock list and alerts.

Done when: buying 10 boxes of 100 screws and selling 37 pieces shows 9 boxes 63 pieces (963 pcs) in every godown view, report and valuation.

## Module 3 — Customer & Supplier Ledger

Build:

- Party master with GSTIN check, address, price list, credit limit, credit days.

- Receive payment: pick invoices to settle, or auto-apply oldest first; partial payments supported.

- Invoice-wise dues and ageing buckets; statement of account as PDF to share on WhatsApp.

- Supplier balances, supplier payments against purchase bills.

- Collection reminders: scheduled WhatsApp/SMS with a UPI payment link; payments via link auto-post to the ledger.

- Today’s collection list for the owner: who to call, how much, how old.

Done when: the ledger balance for any party equals the sum of their open invoices minus unallocated payments, to the paisa.

## Module 4 — Profit & Business Reports

Build:

- Daily sales (by bill, item, category, customer, clerk, payment mode).

- Gross margin by item, category and customer, using weighted average cost.

- Expenses with categories (rent, salary, transport, loading, power) and net profit estimate.

- Outstanding credit (receivables) and payables with ageing.

- Stock valuation (at cost and at retail), dead stock (no sale in 90 days), fast movers.

- Cash reconciliation: open cash, cash sales, cash receipts, cash expenses, expected vs counted at close.

- GST: sales and purchase registers, HSN summary, GSTR-1 export (JSON/Excel), GSTR-3B summary.

- Every report filterable by date range and exportable to Excel and PDF.

Done when: the accountant can file GSTR-1 from the export without retyping, and the day-close cash difference is shown per counter.

## Dashboard

One screen the owner opens each morning: today’s sales, profit estimate, expenses, cash in hand, outstanding receivables (with “overdue” count), payables due this week, low-stock items, and top 5 debtors. Numbers come from pre-computed snapshots refreshed every few minutes, so it opens in under 1 second.

## Module 5 — AI Business Assistant

How it works: the model never writes SQL and never does arithmetic. It picks from a fixed set of safe, tenant-scoped tools, the backend runs them, and the model explains the result in Tamil or English with a table or chart.

| Tool | Answers questions like |
| --- | --- |
| get_receivables(min_days, min_amount) | “Who owes me money?”, “Who is overdue more than 60 days?” |
| profit_by_product(period, top_n) | “Which products made the most profit this month?” |
| reorder_suggestions(godown) | “Which items should I reorder?” |
| sales_summary(period, group_by) | “How were sales this week vs last week?” |
| dead_stock(days) | “What has not sold in 3 months?” |
| customer_summary(name) | “How much has Murugan Constructions bought this year?” |
| payables_due(days) | “Which suppliers do I need to pay this week?” |

Reorder logic: suggested quantity = (average daily sales over the last 30–90 days × supplier lead time days) + safety stock − current stock − quantity already on order, rounded to the purchase unit. Show the reasoning next to each suggestion.

Done when: the 20 most common owner questions (collect them in the pilot) return correct numbers that match the matching report, and every answer shows a “see the report” link.

Later: voice questions (faster-whisper), asking on WhatsApp, and a morning WhatsApp summary to the owner.

# 5. Roadmap and timeline

Ship v1 in 24 weeks across five phases, each ending in a gate you must pass before moving on. The timeline assumes the team in section 6; with only 2 developers, plan for about 32 weeks.

| Phase | Weeks | Scope | Gate to pass |
| --- | --- | --- | --- |
| 0 · Foundations | 1–3 | Tenancy and RLS, auth and roles, number series, CI/CD, core data model; 1-week spike on unit conversion + offline bill + thermal print | The spike prints an offline bill with correct GST and stock |
| 1 · Fast Billing + Smart Inventory | 4–11 | Product master and import, units, price lists, POS billing, quotations, challans, returns; purchases, godowns, adjustments, stock count; desktop counter app with offline sync | A full day of real shop bills replayed with zero stock or GST errors |
| 2 · Ledger + Reports + Dashboard | 12–17 | Party ledger, payment allocation, ageing, WhatsApp reminders with UPI links; sales, margin, expenses, stock valuation, cash close, GSTR-1 export, owner dashboard | The shop accountant files GSTR-1 from the export without retyping |
| 3 · AI Business Assistant | 18–20 | Tool functions, Tamil + English answers, reorder suggestions, query log and feedback; test set of 20 real owner questions | All 20 test questions match the reports exactly |
| 4 · Pilot and launch | 21–24 | 3–5 shops run in parallel for 2 weeks, then switch; fixes, speed, hardened backups; onboarding kit, pricing plan, support process | Go-live: pilot shops bill only on the new system for 2 straight weeks |

The AI assistant is built last on purpose: it can only be trusted once billing, stock and ledger numbers are proven correct in a real shop.

## Sprint plan (2-week sprints)

| Sprint | Weeks | Deliverables | Demo at sprint end |
| --- | --- | --- | --- |
| S0 | 1–3 | Repo, CI/CD, tenancy + RLS, auth, roles, settings, number series; spike on unit conversion, offline bill and thermal print | Offline bill printed on a real thermal printer |
| S1 | 4–5 | Product master, categories, units and conversions, price lists, HSN/GST, Excel import | Import a pilot shop catalogue; view stock in mixed units |
| S2 | 6–7 | POS billing: search, barcode, unit picker, customer price list, discounts, GST, payments, A4 + thermal print, WhatsApp share | 5-line bill in under 30 s |
| S3 | 8–9 | Quotations, delivery challans, sales returns, purchase entry, purchase returns, weighted average cost | Quote → invoice → challan → return round trip |
| S4 | 10–11 | Godowns, transfers, adjustments, stock count, desktop counter app with offline sync | Two counters billing offline, then syncing cleanly |
| S5 | 12–13 | Party ledger, receipts, invoice allocation, credit limits, ageing, statements | Party balance matches open invoices to the paisa |
| S6 | 14–15 | Collection reminders with UPI links, expenses, cash open/close, owner dashboard | Morning dashboard opens in under 1 s |
| S7 | 16–17 | Sales, margin, stock valuation, dead stock, GST registers, HSN summary, GSTR-1 export | Accountant reviews GSTR-1 export |
| S8 | 18–20 | AI tool functions, assistant UI (Tamil + English), reorder suggestions, query log | 20 test questions answered correctly |
| S9 | 21–24 | Pilot in 3–5 shops, bug fixes, speed, backups and restore drill, onboarding kit | Go-live decision |

# 6. Team, testing, pilot and risks

## Team (minimum)

| Role | Count | Owns |
| --- | --- | --- |
| Product lead / architect | 1 | Specs, data model, GST rules, pilot shops |
| Backend developer (FastAPI, Postgres) | 1–2 | Ledger, stock, GST, reports, AI tools |
| Frontend developer (React / Next.js) | 1 | Back office, dashboard, reports UI |
| Full-stack / desktop developer (Tauri, printing, sync) | 1 | Billing counter, offline sync, printers, scanners |
| QA (part-time, from week 8) | 0.5 | Test cases, pilot support |

Write each module spec as an AGENTS.md-style file (entities, rules, edge cases, acceptance tests) before coding, so coding agents and developers build from the same source.

## Testing that matters most

- Money and stock math: golden-file tests for GST splits, round-off, discounts and unit conversion; property tests that stock in base units always equals the sum of movements.

- Ledger integrity: a nightly check that each party balance equals open invoices minus unallocated payments; alert on any mismatch.

- Offline sync: tests for two counters billing the same item offline, a device offline for 3 days, and duplicate pushes.

- Real hardware: test on at least two thermal printer brands, one A4 printer, and two barcode scanners that pilot shops actually use.

- Tenant isolation: automated tests that every API call with tenant A’s token cannot read tenant B’s rows.

## Pilot plan

- Recruit 3–5 shops around Salem with different profiles: pure retail, contractor-heavy, one with 2 godowns.

- Import their products, parties and opening balances for them (a ready-made catalogue of common hardware items with HSN and units saves days).

- Run alongside their current system for 2 weeks, then switch.

- Visit weekly; record every question the owner asks out loud — that list becomes the AI assistant’s test set.

## Risks

| Risk | Mitigation |
| --- | --- |
| Clerks find it slower than their old tool and stop using it | Keyboard-first billing, time every flow in pilot, fix anything over 30 s |
| Wrong GST or stock numbers destroy trust | Golden tests, immutable ledgers, nightly integrity checks |
| Internet outages stop billing | Offline counter app with reserved number series |
| Messy data migration delays go-live | Import tool with preview, plus a prepared hardware catalogue |
| AI gives a wrong number | Model only narrates tool output; every answer links to the report |
| Scope creep into full accounting | Export clean data to Tally / accountant instead of rebuilding accounting in v1 |

## Next steps

- ☐ Lock the data model (section 3) and write module specs for Billing, Inventory and Ledger

- ☐ Line up 3–5 pilot shops and collect their current product lists and printers

- ☐ Build a 1-week spike: unit conversion + offline bill + thermal print on real hardware

- ☐ Decide the product name and pricing plan before pilot